## Sheet1
| Kaizen Checklist |  | https://templatestaff.com
#
1 | Two weeks or more before the kaizen event: | Check | Comments
2 | Identify kaizen event leader (Champion) and Management Sponsor
3 | Choose team members and confirm availability with their managers
4 | Prepare a kaizen event Approach and collect any historical data required to support the kaizen event
5 | Reserve a team room for the kaizen event
One week before the kaizen event:
6 | Sponsor - review and approve the kaizen event Approach
7 | Notify team members that they are on the team (do this early in the week)
8 | Determine who should attend the following events, and invite them:
9 | Management Review, celebration dinner, final presentation
10 | Arrange to buy lunches for the team during the kaizen
One to two days before the kaizen event:
11 | Hold a 10 minute team meeting to gain commitment from each team member
12 | Assure the kaizen event cell/ area is properly scheduled to support planned time observations (representative parts)
13 | Gather any supplies required for the kaizen event (flipcharts, post-it notes, area maps/layouts, area schedules, etc)
14 | Print out copies of the kaizen event Approach for the team
Kaizen event Day 1:
15 | Team training or team building exercise
16 | Review the kaizen event Approach with the team
17 | Discovery – Conduct observations in the kaizen event area
18 | Analysis – Quantify observations and use team tools to do a “before” analysis
Kaizen event Day 2:
19 | Brainstorm – Brainstorming focused on team goals and objectives, based on information collected from the discovery and analysis phases. This usually starts with the full group, which may be broken into smaller sub-teams depending on the kaizen event.
20 | Plan – Soon after lunch, the team should re-group and begin to analyze the ideas they have gathered. This often includes ranking ideas based on impact, cost, and ease of implementation. By mid-afternoon they should have a good idea of what they want to implement as a team.
21 | Management Update – The purpose of this informal review is to get management approval on ideas the team plans to implement that week. In addition, the kaizen event leader may prepare management to use this time to push the team either in a different direction or to be more aggressive in their ideas. The rest of the day (after the review) may be used to begin implementation or to divvy out implementation assignments for the following day.
Kaizen event Day 3 / 4:
22 | Implementation – Team members may work in sub-teams or independently for part of the day, but the team should regroup every 2 hours to make sure we are still on-track and not running into problems. Machine moves or other maintenance requests may be scheduled for overnight completion.
23 | Make a list of the actions/requirements to implement the ideas generated in the brainstorming. Assign team members to work on those actions/requirements. Set specific completion times.
24 | Get people out on the floor or in the work area ! Ideas are brought to life on the shop floor not in the training room. Team members to update the team leader regularly so that modifications of the ideas can be coordinated.
Kaizen event Day 5:
25 | Observation and adjustment – Repeat similar time observation studies to measure improvements, and make adjustments (or continue implementation) as required.
26 | Present Results – Team presents kaizen event results to management team and areas impacted. Presentation should include results and a 30-day follow-up list.
Kaizen event Follow-up:
27 | Team Champion and Management Sponsor….
28 | Regular / weekly update of the 30-day-action list – ensuring assigned people are meeting their assigned obligations.
29 | Regular / weekly audit of kaizen event area to ensure conformance to implementation.
30 | A daily walk through for the first two weeks of the kaizen event between the Champion and area Supervisor to point out non-compliance with the changes and also to commend compliance with the changes.
31 | Coach the supervisor to do the above on his/ her own, questioning and commending the floor persons.
32 | Coach the supervisor to ask for continuous improvement ideas, and implement immediately any ideas that make sense and can be changed easily. This empowers the floor and holds them accountable at the same time.
33 | The champion inviting the appropriate management staff to join in the above mentioned audit can be advantageous.